## Slide 1
jack henry™
JHBI Analytics
FY27 Strategic Roadmap
Q1–Q4 FY27 · Jul 2026 – Jun 2027
The Foundation
The Lens
The Interface
The Engine
For internal use · Executive briefing

## Slide 2
Four Investment Pillars — What We Are Building
JHBI · FY27
jack henry™ · JHBI · Confidential · FY27 · Jul 2026 – Jun 2027
THE FOUNDATION
The Foundation
Data Acquisition
FI behavioral data pipelines from JH core systems
Real-time streaming infrastructure (Kafka / event bus)
Data quality monitoring, lineage & governance framework
Enterprise data catalog and governance framework
Aggregated anonymized FI benchmarking data layer
THE LENS
The Lens
Visualizations
Executive KPI dashboards embedded in JH platform
Model performance & drift monitoring dashboards
FI client-facing risk score explorer (banker fact)
Self-serve analytics surface for business stakeholders
THE INTERFACE
The Interface
App / API Dev
Lightweight internal AI apps embedded in JH ecosystem
REST APIs distributing model scores to JH products
Banno + JH Enterprise integration & alerting workflows
Meeting and workflow automation services layer
Role-based access control and full audit logging
THE ENGINE
The Engine
DS Buildout
ML platform: feature store + experiment tracking
AutoGluon, CatBoost, XGBoost model serving at scale
SHAP explainability layer across all deployed models
Model governance, bias review, and model card process

## Slide 3
JHBI Analytics Team
FY27 Leadership Structure
jack henry™ · JHBI · Confidential · FY27 · Jul 2026 – Jun 2027
Mike Ames
Head of Data Science
NET NEW HEADCOUNT
7
Software Dev
2
Management
5
Data Science
FY26 · 1 Position (MLOps Engineer)
FY27 · 13 Positions
Michael Goolsby
Director, Software Development
[TBD]
Mgr, JHBI Product Mgmt & GTM
[TBD]
Data Science Lead
Data Acq. & Engineering
—
Existing FTEs
—
Contractors
—
New FTEs Req.
Foundation
Visualization
—
Existing FTEs
—
Contractors
—
New FTEs Req.
The Lens
App Dev
—
Existing FTEs
—
Contractors
—
New FTEs Req.
Interface
Elspeth Bloodgood
PM, Go-to-Market & Visualization
The Lens
Ashley Greenhaw
PM, Application Development
Interface
Mike Saunders
PM, Data Acq. & Engineering
Foundation
[PM Function TBD]
—
Existing FTEs
—
Contractors
—
New FTEs Req.
The Engine
Data Scientist
—
Existing FTEs
—
Contractors
—
New FTEs Req.
The Engine
MLOps Engineer
1
Open Position · FY26
The Engine
PILLAR OWNERSHIP
The Foundation
The Lens
The Interface
The Engine
Named hire
[TBD] — planned role
Open position

## Slide 4
JHBI Analytics — Program Overview
Strategic Pillars · FY27
jack henry™ · JHBI · Confidential · FY27 · Jul 2026 – Jun 2027
The Foundation
FI behavioral data pipelines from JH core systems
Real-time streaming infrastructure (Kafka / event bus)
Data quality monitoring, lineage & enterprise catalog
SilverLake
Symitar
Banno
Zelle
ACH
NCUA 5300
The Lens
Executive KPI dashboards embedded in JH platform
Model performance & drift monitoring dashboards
FI risk score explorer & self-serve analytics surface
The Interface
AI apps in JH ecosystem (Churn, Anomaly, Zelle Memo)
REST APIs distributing model scores to JH products
Banno + JH Enterprise integration & alerting workflows
The Engine
AutoGluon, CatBoost, XGBoost model training at scale
SHAP explainability layer across all deployed models
MLOps: CI/CD, model registry, drift monitoring & governance

## Slide 5
JHBI Analytics — Quarterly Roadmap
FY26 H2 Foundation + FY27 · Jan 2026 – Jun 2027
jack henry™ · JHBI · Confidential · FY27 · Jul 2026 – Jun 2027
FY26 H2
Jan–Jun '26
Q1 FY27
Jul–Sep '26
Q2 FY27
Oct–Dec '26
Q3 FY27
Jan–Mar '27
Q4 FY27
Apr–Jun '27
The Foundation
▶ Active
FI Data Pipeline Architecture & Core Banking Connectivity
Core Banking Data Pipeline — FI Connectivity Layer
Data Quality Framework & Lineage Tracking
Real-time Kafka Streaming Infrastructure
Enterprise Data Catalog & Governance Framework
The Lens
▶ Active
Dashboard Design Baseline & KPI Framework
Executive KPI Dashboard — Platform MVP Launch
Risk Score Explorer — Banker-Facing Interface
Model Drift Monitoring & Alert Engine
Self-Serve Analytics Surface — Business Users
The Interface
▶ Active
AI App Architecture & FI Data Access Agreements
Churn Mediation MVP — JH CRM Integration
Zelle Memo Intelligence — NLP Pipeline Live
Call Report AI — Full CU Client Rollout
Account Opening LTV — JH Platform Launch
The Engine
▶ Active
ML Platform: Feature Store, Experiment Tracking & Model Registry
ML Model Serving Infrastructure & Feature Store
Anomaly Detection — Streaming Production Launch
MLOps Pipeline — Full CI/CD & Governance
Cross-Sell Propensity Engine (Horizon Phase 1)

## Slide 6
JHBI Analytics — Gantt Chart
18-Month View · Jan 2026 – Jun 2027
jack henry™ · JHBI · Confidential · FY27 · Jul 2026 – Jun 2027
FY26 H2 · Foundation
Q1 FY27
Q2 FY27
Q3 FY27
Q4 FY27
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
THE FOUNDATION
FI Data Pipeline Architecture & Core Banking Integration
▶ In Progress
Core Banking Pipeline Integration
Core Banking Pipeline …
Data Quality Framework & Enterprise Catalog
Data Quality Framework…
THE LENS
Dashboard Requirements & Design Baseline
▶ In Progress
Executive KPI Dashboard — Platform Launch
Executive KPI Dashboar…
Risk Score Explorer + Drift Monitoring
Risk Score Explorer + …
THE INTERFACE
AI App Architecture & FI Data Access Agreements
▶ In Progress
Churn Mediation + Zelle Memo Intelligence
Churn Mediation + Zell…
Call Report AI Scale + Account Opening LTV
Call Report AI Scale +…
THE ENGINE
ML Platform: Feature Store, Experiment Tracking & Registry
▶ In Progress
Anomaly Detection — Streaming Production
Anomaly Detection — St…
MLOps Pipeline + Horizon App Scoping
MLOps Pipeline + Horiz…
TODAY

## Slide 7
JHBI — Staffing Transition Plan
Contractor Ramp-Down · 3-Wave FTE Conversion
jack henry™ · JHBI · Confidential · FY27 · Jul 2026 – Jun 2027
FY26 H2 · Foundation
Q1 FY27 · Wave 1
Q2 FY27 · Wave 2
Q3 FY27 · Wave 3
Q4 FY27
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
0
2
4
6
8
10
12
14
Headcount
2 FTEs
5 Contractors
Total: 7
Foundation
FY26 H2
5 FTEs
4 Contractors
Total: 9
Wave 1
Q1 FY27
8 FTEs
2 Contractors
Total: 10
Wave 2
Q2 FY27
11 FTEs
Total: 11
Wave 3
Q3+ FY27
▶ Wave 1
▶ Wave 2
▶ Wave 3
FTEs (Full-Time)
Contractors
* Headcount figures are illustrative — update with actuals

## Slide 8
JHBI Analytics — Phase 1 Business Case
FI Value · ARR Scaling · 8,000+ FI Clients
jack henry™ · JHBI · Confidential · FY27 · Jul 2026 – Jun 2027
Churn
Mediation
$1–3M
/yr per FI
15–25% churn reduction
Q1 FY27
Zelle Memo
Intelligence
$250–600K
/yr per FI
60% manual review reduction
Q2 FY27
Anomaly
Detection
$1–2M
/yr per FI
70% false-positive reduction
Q2 FY27
Call
Report AI
$100–300K
/yr per FI
Board prep & peer benchmarking
Q1 FY27
Account
Opening LTV
$500K–1.5M
/yr per FI
3–5× cross-sell lift
Q4 FY27
$3–7.5M / year combined value per FI client · conservative estimate for a mid-size $1B deposits community bank
$19.5M ARR
500 FIs · 6% of JH client base
$78M ARR
2,000 FIs · 25% of JH client base
$312M+ ARR
8,000+ FIs · Full JH client base
ARR estimates based on avg. subscription value across tiers. Adoption rates modeled at 6%, 25%, and 100% of JH’s 8,000+ FI client base. Sources: Mordor Intelligence, ICBA / Cornerstone 2025 survey.

## Slide 9
JHBI Analytics — FY27 Quarterly View
Q1–Q4 FY27 | Alternate Layout
jack henry™ · JHBI · Confidential · FY27 · Jul 2026 – Jun 2027
FY27 Q1
Jul–Sep '26
The Foundation
Core Banking Data Pipeline — FI Connectivity Layer
The Lens
Executive KPI Dashboard — Platform MVP Launch
The Interface
Churn Mediation MVP — JH CRM Integration
The Engine
ML Model Serving Infrastructure & Feature Store
FY27 Q2
Oct–Dec '26
The Foundation
Data Quality Framework & Lineage Tracking
The Lens
Risk Score Explorer — Banker-Facing Interface
The Interface
Zelle Memo Intelligence — NLP Pipeline Live
The Engine
Anomaly Detection — Streaming Production Launch
FY27 Q3
Jan–Mar '27
The Foundation
Real-time Kafka Streaming Infrastructure
The Lens
Model Drift Monitoring & Alert Engine
The Interface
Call Report AI — Full CU Client Rollout
The Engine
MLOps Pipeline — Full CI/CD & Governance
FY27 Q4
Apr–Jun '27
The Foundation
Enterprise Data Catalog & Governance Framework
The Lens
Self-Serve Analytics Surface — Business Users
The Interface
Account Opening LTV — JH Platform Launch
The Engine
Cross-Sell Propensity Engine (Horizon Phase 1)